## Tasks
Digital Elevator_PP_Tasks
[9 empty] | 2020-01-01 | [10 empty] | 2020-02-01
[9 empty] | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
# | Member Name | Task Name | Task Description | Task Type | Start Date | Deadline | Submission Date | Comments | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
1 | Nouran Mamdouh | SRS-Document | Initiaing the SRS Document | Non-Technical | 22-1-2020 | 22-1-2020 | 23-1-2020 | - | bar: 2020-01-01 22 to 2020-01-01 23
2 | Donia Mohamed | CYRS-Document | Initiaing the CYRS Document | Non-Technical | 21-1-2020 | 21-1-2020 | 22-1-2020 | - | bar: 2020-01-01 21 to 2020-01-01 22
3 | Ahmed Refaat | HSI-Document | Initiaing the HSI Document | Non-Technical | 22-1-2020 | 22-1-2020 | 24-1-2020 | - | bar: 2020-01-01 22 to 2020-01-01 24
4 | Islam El-Bahnasawy | SRS-Document | Initiaing the SRS Document | Non-Technical | 22-1-2020 | 22-1-2020 | 23-1-2020 | - | bar: 2020-01-01 22 to 2020-01-01 23
5 | Marcelle Samir | HSI-Document | Initiaing the HSI Document | Non-Technical | 22-1-2020 | 22-1-2020 | 24-1-2020 | - | bar: 2020-01-01 22 to 2020-01-01 24
6 | Donia Mohamed | CYRS-Modifications | Applying the suggested modifications from the CYRS_Review sheet to the CYRS Document | Non-Technical | 24-1-2020 | 26-1-2020 | 24-1-2020 | - | bar: 2020-01-01 24 to 2020-01-01 25
7 | Nouran Mamdouh | SRS-Modifications | Modifing the SRS Document acoording to the suggested modifications from the SRS_Review sheet | Non-Technical | 26-1-2020 | 30-1-2020 | 31-1-2020 | - | bar: 2020-01-01 26 to 2020-01-01 31
8 | Islam El-Bahnasawy | SRS-Modifications | Modifing the SRS Document acoording to the suggested modifications from the SRS_Review sheet | Non-Technical | 26-1-2020 | 30-1-2020 | 31-1-2020 | - | bar: 2020-01-01 26 to 2020-01-01 31
9 | Ahmed Refaat | HSI-Modifications | Modifing the HSI Document acoording to the suggested modifications from the HSI_Review sheet | Non-Technical | 26-1-2020 | 29-1-2020 | 28-1-2020 | - | bar: 2020-01-01 26 to 2020-01-01 28
10 | Marcelle Samir | HSI-Modifications | Modifing the HSI Document acoording to the suggested modifications from the HSI_Review sheet | Non-Technical | 26-1-2020 | 29-1-2020 | 28-1-2020 | - | bar: 2020-01-01 26 to 2020-01-01 28
11 | Donia Mohamed | CYRS-Modifications | Modifing the CYRS Document acoording to the suggested modifications from the last meeting (1-2-2020) | Non-Technical | 3-2-2020 | 5-2-2020 | 5-2-2020 | - | bar: 2020-02-01 3 to 2020-02-01 5
12 | Nouran Mamdouh | SRS-Modifications | Modifing the SRS Document acoording to the suggested modifications from the last meeting (1-2-2020) | Non-Technical | 5-2-2020 | 7-2-2020 | 6-2-2020 | - | bar: 2020-02-01 5 to 2020-02-01 6
13 | Islam El-Bahnasawy | SRS-Modifications | Modifing the SRS Document acoording to the suggested modifications from the last meeting (1-2-2020) | Non-Technical | 5-2-2020 | 7-2-2020 | 6-2-2020 | - | bar: 2020-02-01 5 to 2020-02-01 6
14 | Ahmed Refaat | HSI-Modifications | Modifing the HSI Document acoording to the suggested modifications from the last meeting (1-2-2020) | Non-Technical | 3-2-2020 | 5-2-2020 | 5-2-2020 | - | bar: 2020-02-01 3 to 2020-02-01 5
15 | Marcelle Samir | HSI-Modifications | Modifing the HSI Document acoording to the suggested modifications from the last meeting (1-2-2020) | Non-Technical | 3-2-2020 | 5-3-2020 | 5-2-2020 | - | bar: 2020-02-01 3 to 2020-02-01 5
16 | Donia Mohamed | CYRS-Modifications | Modifing the CYRS Document acoording to our last team review meeting (6-2-2020) | Non-Technical | 6-2-2020 | 7-2-2020 | 7-2-2020 | - | bar: 2020-02-01 6 to 2020-02-01 7
17 | Nouran Mamdouh | SRS-Modifications | Modifing the SRS Document acoording to our last team review meeting (6-2-2020) | Non-Technical | 6-2-2020 | 7-2-2020 | 7-2-2020 | - | bar: 2020-02-01 6 to 2020-02-01 7
18 | Islam El-Bahnasawy | SRS-Modifications | Modifing the SRS Document acoording to our last team review meeting (6-2-2020) | Non-Technical | 6-2-2020 | 7-2-2020 | 7-2-2020 | - | bar: 2020-02-01 6 to 2020-02-01 7
19 | Ahmed Refaat | HSI-Modifications | Modifing the HSI Document acoording to our last team review meeting (6-2-2020) | Non-Technical | 6-2-2020 | 7-2-2020 | 7-2-2020 | - | bar: 2020-02-01 6 to 2020-02-01 7
20 | Marcelle Samir | HSI-Modifications | Modifing the HSI Document acoording to our last team review meeting (6-2-2020) | Non-Technical | 6-2-2020 | 7-3-2020 | 7-3-2020 | - | bar: 2020-02-01 6 to 2020-02-01 7
21 | Nouran Mamdouh | SRS-Modifications | Modifing the SRS Document by adding the context diagram | Non-Technical | 17-2-2020 | 20-2-2020 |  | - | bar: 2020-02-01 17
22 | Islam El-Bahnasawy | SRS-Modifications | Modifing the SRS Document by adding the context diagram | Non-Technical | 17-2-2020 | 20-2-2020 |  | - | bar: 2020-02-01 17
23
24
25
Progress
Late Delivery
Early Delivery

## Time Line
Digital Elevator_PP_Time Line
# | Milestone | Planned Start Date | Actual Start Date | Planned End | Actual End
1 | CYRS_v1.0 | 21-1-2020 | 21-1-2020 | 21-1-2020 | 22-1-2020
2 | SRS_v1.0 | 21-1-2020 | 21-1-2020 | 21-1-2020 | 24-1-2020
3 | HIS_v1.0 | 21-1-2020 | 21-1-2020 | 21-1-2020 | 24-1-2020
4 | RTM_v1.0 | 21-1-2020 | 21-1-2020 | 21-1-2020 | 24-1-2020
5 | CYRS_v1.1 | 24-1-2020 | 24-1-2020 | 26-1-2020 | 25-1-2020
6 | SRS_v1.1 | 26-1-2020 | 26-1-2020 | 30-1-2020 | 31-1-2020
7 | HIS_v1.1 | 26-1-2020 | 26-1-2020 | 29-1-2020 | 28-1-2020
8