## Introduction
Project Name |  |  | Digital Elevator
Ref Document |  | CYRS
Ref Version |  | 1.1
Auther |  | Tarek Sharaby
Last update |  | 23/01/2020
History
Version | Auther |  | Date | Change
0.1 | T.Sharaby |  | 23/01/2020 | Initial creation

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
23/01/2020 | T.Sharaby | V1.1 | CYRS | Page 1 | Document statuc table : you should put the status of the document which exist in the start in a table , this table holds the following info "Document name , Suther , Version , Auther , Last update Date" | Accepted | Open
23/01/2020 | T.Sharaby | V1.1 | CYRS | Revision History | First creation should not be proposed , it should be draft and after the cross review is done and points fixed then it could be proposed , because as I can see both version are proposed , and the change it only the formate so it should stay Draft | Accepted | Open |  | Accepted
23/01/2020 | T.Sharaby | V1.1 | CYRS | Project decription | The decription is very detailed even mention every detail in the project while it should be global over view of the system as it could mention the function provided - Secure Calling - Up and down movement - On / off ,and Rest option then in the requiement level you can mention all details | Accepted | Open |  | Refused
23/01/2020 | T.Sharaby | V1.1 | CYRS | Flow chart | In the CYRS which is system level ther is not flow chart , you can make it system context how system wise blocks will communicate Ex : you have Keypad , Mc , LCD , Push buttons , so you can draw overall system not to mention how it work like if it is software level | Accepted | Open
23/01/2020 | T.Sharaby | V1.1 | CYRS | Req_DIGELV_CYRS_01_V1.0 | you can remove the part "This requirement describe the max" , because it has nomeaning as you already making a req to mention how many user , instead you can say for Ex: The supported Number of usres are 10 by Max and that is it | Accepted | Open |  | Open
23/01/2020 | T.Sharaby | V1.1 | CYRS | ALL | For each Req you can make a table to hold the infor the Req , Ex: Req ID : xxxxxx Title : here you can add the part you mention this req is to do xxxx Description : Here you add the req You don't have to say: this req is to do ……., you can mention what is needed by the requirment directly Ex : Req ID : Req _ DIGELV _CYRS_02_V1.0 Title : Limitiaion for each User Description : Each User has Username and Password , Username of 10 characters By max , and Password of 4 digits , the User name has to be unique , to be set at the first time | Accepted | Open |  | Resolved
23/01/2020 | T.Sharaby | V1.1 | CYRS | ALL | The section before the Req ID is not correct , if you want to make a section then mention what this req title | Accepted | Open
23/01/2020 | T.Sharaby | V1.1 | CYRS | Reference document table | Ref document table is missing , you should add table for the reference document Ref Document : version : status -------------------------------------- Customer Req : xx : xx if the version of the refernce document is not exist or status keep this fields empty | Accepted | Resolved
[9 empty] | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open