## Introduction
Project Name |  |  | Digital Elevator
Ref Document |  | HSI
Ref Version |  | 1
Auther |  | Tarek Sharaby
Last update |  | 24/01/2020
History
Version | Auther |  | Date | Change
0.1 | T.Sharaby |  | 24/01/2020 | Initial creation

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
24/01/2020 | T.Sharaby | V1.0 | HSI_ | Page 1 | Document status table : you should put the status of the document which exist in the start in a table , this table holds the following info "Document name , Suther , Version , Auther , Last update Date" | Accepted | Open
24/01/2020 | T.Sharaby | V1.0 | HSI_ | Revision History | First creation should not be proposed , it should be draft and after the cross review is done and points fixed then it could be proposed , because as I can see both version are proposed , and the change it only the formate so it should stay Draft | Accepted | Open |  | Accepted
24/01/2020 | T.Sharaby | V1.0 | HSI_ | ALL | The aim of HIS_ is to define all req related to HW : Ex : - List all HW needed - Draw block diagrame for how HW will be connected and communicate - Describe all HW - SW interface : system should use Button 1 as Up move ,, and so on | Accepted | Open |  | Refused
24/01/2020 | T.Sharaby | V1.0 | HSI_ | ALL | There is no mention for On/Off button you just mention system will have only 2 buttons | Accepted | Open
24/01/2020 | T.Sharaby | V1.0 | HSI_ | ALL | Req _ DIGELV _ HSI _03_V1.0 : what is the goal of this req ? If you should say the system Keypad to enter the pass and ID for the input and LCD to display the out put , but here you refere to CYRS req , Why ? ,,, you don't have to | Accepted | Open |  | Open
Resolved
[9 empty] | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open