## Introduction
Project Name |  |  | Digital Elevator
Ref Document |  | GDD
Ref Version |  | 1
Author |  | Moustafa Ghareeb
Last update |  | 6/3/2020
History
Version | Author |  | Date | Change
0.1 | Moustafa Ghareeb |  | 6/3/2020 | Initial creation

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
6/3/2020 | MGH | V1.2 | GDD | 8 | Software features needs modification: - The signals names should be mentioned also the diagram should implement the sw prespective so the communication between the components should be revised |  | Open
6/3/2020 | MGH | V1.2 | GDD | whole APIs section | APIs: Copy_u32Port doesn't need to be a u32 it could be u8 only |  | Open |  | Accepted
6/3/2020 | MGH | V1.2 | GDD | whole APIs section | APIs: should handel pins not port and pin to be more abstracted |  | Open |  | Refused
6/3/2020 | MGH | V1.2 | GDD | whole APIs section | APIs: DIO_Init could be a public API and remove the DIO_SetDIr where it could be called initially |  | Open
6/3/2020 | MGH | V1.2 | GDD | whole APIs section | APIs: Covers part should be added |  | Open |  | Open
6/3/2020 | MGH | V1.2 | GDD | whole APIs section | APIs: Remove ";" from the API prototype |  | Open |  | Resolved
[9 empty] | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open