## Introduction
Project Name |  |  | Digital Elevator
Ref Document |  | SRS
Ref Version |  | 1.1
Auther |  | Tarek Sharaby
Last update |  | 2020-07-02
History
Version | Auther |  | Date | Change
0.1 | T.Sharaby |  | 27/01/2020 | Initial creation
0.2 | T.Sharaby |  | 2020-07-02 | Add some pints

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
27/01/2020 | TSH | V1.0 | SRS | 1 | You should manage the status table of the document as follows : Document : xxxxxx Auther : xxxxxx Date : xxxxxx "fo last update " Version : xxxx Status : Darfte , Proposed , Reviewed , Released | Accepted | Open
27/01/2020 | TSH | V1.0 | SRS | Revision History | At the creation of the document it should be draft , then after first cross review and fixing the open points you can changed it to Proposed | Accepted | Open |  | Accepted
27/01/2020 | TSH | V1.0 | SRS | ALL | There is no refernce table for the refernce document it should be like this : Ref Docu : xxxxx Version : xxxx Status : xxx Ex the reference for SRS means the input document that enables you to meke the SRS , so the inputs are : - CYRS , and HIS_ if it contains SW req , if not then CYRS is the input for SRS | Accepted | Open |  | Refused
27/01/2020 | TSH | V1.0 | SRS | ALL | There is no Software context which decrib the blocks of SW how they are going to communicate in terms of sw features |  | Open
27/01/2020 | TSH | V1.0 | SRS | Software requirement | The goal of the SW req is to descrip what in specific software shall do , so you shall keep the SRS req atmoic means do one thing , and try to make an input and out put for it as much as you can | Accepted | Open |  | Open
27/01/2020 | TSH | V1.0 | SRS | Software requirement | you could represent each req in a table for more organization this table as follows : Req ID : xxx Description : xxxxxx Coverage : the CYRS req Input : xxx if you have it output : if you have |  | Open |  | Resolved
27/01/2020 | TSH | V1.0 | SRS | Software requirement | DIGELV_SRS_001_V1.0: for instance this req could be divided in several parts - Software shall accept number of users from 0 to Config_NumbOfUsers , "Config_NumbOfUsers = 10" - when Signal_UserNum is more than Config_NumbOfUsers , the SW shall reject the input and make Signal_ErrorFlag True - etc Here I ttried to consider I have 2 feature in the SW talking with signals : 1- Input acquistion : this get the Signal_UserNum from Keypad as an input and process then give Signal_ErrorFlag as an output 2- Display output: this one will take the Error flag as an input and process it then update the LCD , and so on | Accepted | Open
2020-07-02 | TSH | V1.1 | SRS | Software requirement | At the first page it says the version is 1.0 and it is proposed , but the in history it is 1.1 |  | Open
2020-07-02 | TSH | V1.1 | SRS | Software requirement | Still not all rebiew points resolved |  | Open |  | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open