## Tasks
Digital Elevator_PP_Tasks
[9 empty] | 2020-01-01 | [10 empty] | 2020-02-01 | [21 empty] | 2020-03-01
[9 empty] | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
# | Member Name | Task Name | Task Description | Task Type | Start Date | Deadline | Submission Date | Comments | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | S | M | T | W
1 | Nouran Mamdouh | SRS-Document | Initiaing the SRS Document | Non-Technical | 22-1-2020 | 22-1-2020 | 23-1-2020 | - | bar: 2020-01-01 22 to 2020-01-01 23
2 | Donia Mohamed | CYRS-Document | Initiaing the CYRS Document | Non-Technical | 21-1-2020 | 21-1-2020 | 22-1-2020 | - | bar: 2020-01-01 21 to 2020-01-01 22
3 | Ahmed Refaat | HSI-Document | Initiaing the HSI Document | Non-Technical | 22-1-2020 | 22-1-2020 | 24-1-2020 | - | bar: 2020-01-01 22 to 2020-01-01 24
4 | Islam El-Bahnasawy | SRS-Document | Initiaing the SRS Document | Non-Technical | 22-1-2020 | 22-1-2020 | 23-1-2020 | - | bar: 2020-01-01 22 to 2020-01-01 23
5 | Marcelle Samir | HSI-Document | Initiaing the HSI Document | Non-Technical | 22-1-2020 | 22-1-2020 | 24-1-2020 | - | bar: 2020-01-01 22 to 2020-01-01 24
6 | Donia Mohamed | CYRS-Modifications | Applying the suggested modifications from the CYRS_Review sheet to the CYRS Document | Non-Technical | 24-1-2020 | 26-1-2020 | 24-1-2020 | - | bar: 2020-01-01 24 to 2020-01-01 25
7 | Nouran Mamdouh | SRS-Modifications | Modifing the SRS Document acoording to the suggested modifications from the SRS_Review sheet | Non-Technical | 26-1-2020 | 30-1-2020 | 31-1-2020 | - | bar: 2020-01-01 26 to 2020-01-01 31
8 | Islam El-Bahnasawy | SRS-Modifications | Modifing the SRS Document acoording to the suggested modifications from the SRS_Review sheet | Non-Technical | 26-1-2020 | 30-1-2020 | 31-1-2020 | - | bar: 2020-01-01 26 to 2020-01-01 31
9 | Ahmed Refaat | HSI-Modifications | Modifing the HSI Document acoording to the suggested modifications from the HSI_Review sheet | Non-Technical | 26-1-2020 | 29-1-2020 | 28-1-2020 | - | bar: 2020-01-01 26 to 2020-01-01 28
10 | Marcelle Samir | HSI-Modifications | Modifing the HSI Document acoording to the suggested modifications from the HSI_Review sheet | Non-Technical | 26-1-2020 | 29-1-2020 | 28-1-2020 | - | bar: 2020-01-01 26 to 2020-01-01 28
11 | Donia Mohamed | CYRS-Modifications | Modifing the CYRS Document acoording to the suggested modifications from the last meeting (1-2-2020) | Non-Technical | 3-2-2020 | 5-2-2020 | 5-2-2020 | - | bar: 2020-02-01 3 to 2020-02-01 5
12 | Nouran Mamdouh | SRS-Modifications | Modifing the SRS Document acoording to the suggested modifications from the last meeting (1-2-2020) | Non-Technical | 5-2-2020 | 7-2-2020 | 6-2-2020 | - | bar: 2020-02-01 5 to 2020-02-01 6
13 | Islam El-Bahnasawy | SRS-Modifications | Modifing the SRS Document acoording to the suggested modifications from the last meeting (1-2-2020) | Non-Technical | 5-2-2020 | 7-2-2020 | 6-2-2020 | - | bar: 2020-02-01 5 to 2020-02-01 6
14 | Ahmed Refaat | HSI-Modifications | Modifing the HSI Document acoording to the suggested modifications from the last meeting (1-2-2020) | Non-Technical | 3-2-2020 | 5-2-2020 | 5-2-2020 | - | bar: 2020-02-01 3 to 2020-02-01 5
15 | Marcelle Samir | HSI-Modifications | Modifing the HSI Document acoording to the suggested modifications from the last meeting (1-2-2020) | Non-Technical | 3-2-2020 | 5-3-2020 | 5-2-2020 | - | bar: 2020-02-01 3 to 2020-02-01 5
16 | Donia Mohamed | CYRS-Modifications | Modifing the CYRS Document acoording to our last team review meeting (6-2-2020) | Non-Technical | 6-2-2020 | 7-2-2020 | 7-2-2020 | - | bar: 2020-02-01 6 to 2020-02-01 7
17 | Nouran Mamdouh | SRS-Modifications | Modifing the SRS Document acoording to our last team review meeting (6-2-2020) | Non-Technical | 6-2-2020 | 7-2-2020 | 7-2-2020 | - | bar: 2020-02-01 6 to 2020-02-01 7
18 | Islam El-Bahnasawy | SRS-Modifications | Modifing the SRS Document acoording to our last team review meeting (6-2-2020) | Non-Technical | 6-2-2020 | 7-2-2020 | 7-2-2020 | - | bar: 2020-02-01 6 to 2020-02-01 7
19 | Ahmed Refaat | HSI-Modifications | Modifing the HSI Document acoording to our last team review meeting (6-2-2020) | Non-Technical | 6-2-2020 | 7-2-2020 | 7-2-2020 | - | bar: 2020-02-01 6 to 2020-02-01 7
20 | Marcelle Samir | HSI-Modifications | Modifing the HSI Document acoording to our last team review meeting (6-2-2020) | Non-Technical | 6-2-2020 | 7-3-2020 | 7-3-2020 | - | bar: 2020-02-01 6 to 2020-02-01 7
21 | Nouran Mamdouh | SRS-Modifications | Modifing the SRS Document by adding the context diagram | Non-Technical | 17-2-2020 | 20-2-2020 | 20-2-2020 | Partially done | bar: 2020-02-01 17 to 2020-02-01 20
22 | Islam El-Bahnasawy | SRS-Modifications | Modifing the SRS Document by adding the context diagram | Non-Technical | 17-2-2020 | 20-2-2020 | 20-2-2020 | Partially done | bar: 2020-02-01 17 to 2020-02-01 20
23 | Nouran Mamdouh | SRS-Modifications | Modifing the SRS Document by modifing the context diagram | Non-Technical | 21-2-2020 | 22-2-2020 | 23-2-2020 | - | bar: 2020-02-01 21 to 2020-03-01 23
24 | Islam El-Bahnasawy | SRS-Modifications | Modifing the SRS Document by updating the requirements according to the reviewer comments | Non-Technical | 21-2-2020 | 22-2-2020 | 22-2-2020 | - | bar: 2020-02-01 21 to 2020-02-01 22
25 | Donia Mohamed | SRS-Review | Reviewing the SRS document | Non-Technical | 23-2-2020 | 23-2-2020 | 23-2-2020 | Context diagram needs modifications and test scope needs removing | bar: 2020-03-01 23
26 | Nouran Mamdouh | SRS-Modifications | Modifing the SRS Document by modifing the context diagram | Non-Technical | 24-2-2020 | 25-2-2020 | 26-2-2020 | - | bar: 2020-03-01 24 to 2020-03-01 26
27 | Islam El-Bahnasawy | SRS-Modifications | Modifing the SRS Document by removing test scopes section | Non-Technical | 24-2-2020 | 25-2-2020 | 25-2-2020 | - | bar: 2020-03-01 24 to 2020-03-01 25
28 | Donia Mohamed | GDD-Creation | Initiating the GDD document | Non-Technical | 23-2-2020 | 25-2-2020 | 26-2-2020 | - | bar: 2020-03-01 23 to 2020-03-01 25
29 | Ahmed Refaat | GDD-Modifications | Creating the static architecture section in the GDD | Non-Technical | 25-2-2020 | 26-2-2020 | 26-2-2020 | - | bar: 2020-03-01 25 to 2020-03-01 26
30 | Marcelle Samir | GDD-Modifications | Creating the APIs section in the GDD | Non-Technical | 25-2-2020 | 26-2-2020 | 27-2-2020 | - | bar: 2020-03-01 25 to 2020-03-01 27
31 | Donia Mohamed | GDD-Modifications | Updating the signals table and correcting the GDD documents header | Non-Technical | 28-2-2020 | 28-2-2020 | 28-2-2020 | - | bar: 2020-03-01 27
32 | Marcelle Samir | GDD-Modifications | Updating the APIs section in the GDD | Non-Technical | 28-2-2020 | 29-2-2020 | 1-3-2020 | - | bar: 2020-03-01 28 to 2020-03-01 1
33 | Donia Mohamed | GDD-Modifications | Adding the inputs and outputs diagram | Non-Technical | 1-3-2020 | 3-3-2020 |  | - | bar: 2020-03-01 1 to 2020-03-01 2
34 | Marcelle Samir | GDD-Modifications | Completing the APIs section in the GDD | Non-Technical | 1-3-2020 | 4-3-2020 |  | - | bar: 2020-03-01 1 to 2020-03-01 2
35 | Ahmed Refaat | CDD-DIO-Creation | Initiating the CDD document for the DIO driver | Non-Technical | 1-3-2020 | 5-3-2020 | bar: 2020-03-01 1 to 2020-03-01 2
36 | Islam El-Bahnasawy | CDD-LCD-Creation | Initiating the CDD document for the LCD driver | Non-Technical | 1-3-2020 | 5-3-2020 | bar: 2020-03-01 1 to 2020-03-01 2
37 | Moustafa Ghareeb | PCB-Creation | Creating the PCB schematic and board for the system | Technical | 2-3-2021 | 15-3-2021
Progress
Late Delivery
Early Delivery

## Time Line
Digital Elevator_PP_Time Line
# | Milestone | Planned Start Date | Actual Start Date | Planned End | Actual End
1 | CYRS_v1.0 | 21-1-2020 | 21-1-2020 | 21-1-2020 | 22-1-2020
2 | SRS_v1.0 | 21-1-2020 | 21-1-2020 | 21-1-2020 | 24-1-2020
3 | HSI_v1.0 | 21-1-2020 | 21-1-2020 | 21-1-2020 | 24-1-2020
4 | RTM_v1.0 | 21-1-2020 | 21-1-2020 | 21-1-2020 | 24-1-2020
5 | CYRS_v1.1 | 24-1-2020 | 24-1-2020 | 26-1-2020 | 25-1-2020
6 | SRS_v1.1 | 26-1-2020 | 26-1-2020 | 30-1-2020 | 31-1-2020
7 | HSI_v1.1 | 26-1-2020 | 26-1-2020 | 29-1-2020 | 28-1-2020
8 | CYRS_v1.4 | 3-2-2020 | 3-2-2020 | 5-2-2020 | 5-2-2020
9 | HSI_v1.5 | 6-2-2020 | 6-2-2020 | 7-3-2020 | 7-3-2020
10 | GDD_v1.0 | 23-2-2020 | 23-2-2020 | 26-2-2020 | 26-2-2020
11 | GDD_v1.1 | 28-2-2020 | 28-2-2020 | 29-2-2020 | 1-3-2020
12
13
14
15
16
17
18
19
20